## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-03-06-Fantastech
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Helper I want to add/remove needs from my funding basket so that I can change the status of available needs. | GIVEN I add a **need **object to the checkout basket WHEN a **need **with the given name already exists in the checkout basket THEN the system should return a status code of 409 (CONFLICT)
GIVEN I add a **need **object to the checkout basket WHEN a **need **with the given name DOES NOT exist in the checkout basket THEN the system should return a successful status code.
As a Helper I want to add needs from my funding basket so that I can change the status of available needs. | GIVEN I submit a need object from my funding basket WHEN no need with the given name currently exists in the cupboard THEN the system should create the need, add it to the cupboard, and return the need object with a status code of 201 (CREATED)
GIVEN I submit a need object from my funding basket WHEN a need with the same name already exists in the cupboard THEN the system should reject the request, not create a duplicate, and return a status code of 409 (CONFLICT)
GIVEN I submit a valid need object from my funding basket WHEN the system successfully processes it THEN the need status should update from available to funded, and the change should be reflected in the cupboard
As a Helper I want to review all the needs currently in my funding basket so that I can confirm, update, or remove them before finalizing their status. | GIVEN I open my funding basket. WHEN there are one or more needs inside. THEN the system should display a list of all needs with their details (name, description, status).
GIVEN I am viewing my funding basket. WHEN I select a need. THEN I should be able to either update its details, remove it, or proceed to change its status.
GIVEN I remove a need from the basket. WHEN the system processes the request. THEN the need’s status should revert to available, and the basket view should update immediately.
GIVEN I confirm the basket. WHEN I finalize the action. THEN the system should persist all changes and return a success code of 200 (OK).
As a Helper I want to search for a particular need so that I can easily find what things exist or do not exist. | GIVEN I enter a valid search term for a need. WHEN one or more matching needs exist in the cupboard. THEN the system should return a list of matching needs with their details and respond with status code 200 (OK)
GIVEN I enter a search term for a need. WHEN no matching needs exist in the cupboard. THEN the system should return an empty result set with a clear message and respond with status code 200 (OK)
As a U-fund Manager, I want to log in using the reserved username admin so that I can manage the organization's needs cupboard. | GIVEN I submit the reserved username admin with the correct password. WHEN the system validates the credentials. THEN I should be logged in, granted administrator privileges, and receive a status code of 200 (OK)
GIVEN I submit the reserved username admin with an incorrect password. WHEN the system validates the credentials. THEN the login should fail, no access should be granted, and the system should return a status code of 401 (UNAUTHORIZED)
As a Helper I want to edit the details of an existing need in the cupboard | GIVEN I submit an update request for an existing need with valid changes (e.g., name, status, or quantity). WHEN the system finds the need in the cupboard. THEN the system should update the need, persist the changes, and return the updated need object with a status code of 200 (OK)
GIVEN I submit an update request for a need. WHEN the system cannot find a matching need in the cupboard. THEN the system should reject the request and return a status code of 404 (NOT FOUND)